## Sheet1
ID | Asset | Threat | Vulnerability | Likelihood | Impact | Risk Level | Existing Controls | Treatment Plan | Responsible Owner | Timeline
1 | Customer Database | Unauthorized access | Weak password policy | High | High | High | None | Implement strong access controls & MFA | IT Security Manager | 30 days
2 | Cloud Infrastructure | DDoS Attack | No mitigation in place | Medium | High | High | None | Enable DDoS protection with provider | Network Team Lead | 14 days
3 | Employee Laptops | Malware infection | No endpoint protection | High | Medium | High | Antivirus in pilot phase | Deploy EDR solution to all devices | IT Ops Lead | 45 days
4 | Source Code | Insider threat | No monitoring/logging | Medium | High | High | Manual code reviews | Enable audit trails and SOC alerts | DevSecOps | 60 days
5 | Email System | Phishing | No training/awareness | High | Medium | High | Spam filters active | Conduct phishing simulation & awareness training | HR & CISO | 30 days
6 | Backup Servers | Ransomware | No offline backups | Medium | High | High | Daily automated backups | Add offline & immutable backups | Infra Manager | 20 days
7 | HR Records | Data leak | Public sharing via email | Medium | Medium | Medium | Access-controlled folder | Restrict sharing & enforce DLP | HR Manager | 30 days
8 | Development Environment | Zero-day exploits | Unpatched systems | Medium | High | High | Monthly patching | Switch to automated patch management | SysAdmin | 60 days
9 | Network Devices | Physical tampering | No surveillance | Low | Medium | Medium | Locked server room | Add CCTV and access logs | Admin Team | 90 days
10 | Remote Work Tools | Account compromise | Reused passwords | High | High | High | Password policy enforced | Enforce SSO + MFA + Password vault | Security Analyst | 21 days